## Overview
SEPD Whole System Register Overview
This register provides a consolidated list of the engagement and activities SEPD has undertaken over the past year (May 2023 - May 2024) with other network licensees and network users to improve the efficiency of its network and the wider electricity system. This is the first time we have published such a register. By doing so, it is hoped that we can build on and learn from the whole system activities of the past year to improve our future engagements and processes, but also lend transparency to other network licensees and network users on the whole system coordination and cooperation activities happening across the industry and inform future whole system efforts. To aid consistency, the format of the register was agreed between network licensees through the Energy Networks Association. However, we have aligned and organised the contents of our register according to our four priorities: (i) To deliver a safe, resilient and responsive network; (ii) To provide a valued and trusted service for our customers and communities; (iii) To accelerate progress towards a net zero world; and (iv) To make a positive impact on society. We are continually looking to drive and deliver opportunities that will benefit our customers through innovation, cost efficiency, meeting net zero targets etc. Although this register highlights the areas of work that we are currently developing and implementing, we are aware that there are more opportunities that can be realised. If you believe that you can support any of the work we have highlighted within this register, or if you believe that there are opportunities that we should consider, please contact us via the following e-mail address:
Whole System - SSEN
May 2024
Version 1.0

## Activities & Actions
Relevant coordination and cooperation activities | [15 empty] | Actions or Processes arising
SSEN Distribution Priorities Colour Code | Unique ID | Licensee | Collaborating licensees and other stakeholders | Description of the coordination/ cooperation activity | Status | Latest stage /Update /comments (if any) | Coordination activity initiation date (mm/yyyy) | Whole system relevance of the activity | External links to reports on the activity (If available) | Description of data (who shared the data) [widely shared/restricted sharing] | External links for data (if available) | Impact of the activity on the whole system | Impact of the activity on licensee | Recommended next stage of the activity | Justification for recommendation | Action or Process description | Action or process initiation date (mm/yyyy) | Status | Reference of the activity or user suggestion which resulted in this action/process
| SEPD/001 | SEPD | Low Carbon Hub, University of Oxford, Oxfordshire and Oxford City Councils, Origami Energy, Piclo, NuvveCorporation, EDF Energy | LEO is a collaborative DSO demonstrator project involving multiple partners. The objectives are to: (i) prove Investable Business Models; (ii) build a Community of Skilled Energy People in Oxfordshire; (iii) develop the Markets for DSO; (iv) develop the mapping tools for Local Area Energy Planning; and (v) trial flexibility. | Completed | A final report has been produced and final events in the Houses of Parliament and Oxford were held to publish the findings. | 04/2019 | This is a whole systems project, engaging all network licensees (including the ESO) via the ENA and interacting with Suppliers, Aggregators, Local Generation and Demand Sites. | Home - Project LEO (project-leo.co.uk) https://ssen-transition.com/ | There is a data sharing agreement within the project. The holder of the data is ultimately the University of Oxford. | N/A | The LEO project will enable us and other network operators to manage electricity networks more efficiently and flexibly at a local level through positive and broad engagement. | Positive impact through collaboration to enable the energy transition. | Project activities have formally ceased however a number of "spin-off" projects are in development around proposals such as: LEO (N) that has successfully bid for SIF funding. - Understanding the impact of a high density of heat pumps installed around a secondary substation. - The potential to "future-fit" homes and the impact this will have on the network etc. | To further enable a Just Transition and to support councils contribute towards their Net Zero goals. | Looking to apply for SIF funding | 09/2022 | Mature | Project LEO-N in entry SEPD/016 is a direct result of this action.
| SEPD/002 | SEPD | The ESO, NGET, SPEN, NGED, NGN, Arup | SIF project supporting the development of a Virtual Energy System - a programme creating a digital replica of the GB energy system. Involving multiple network licensees and the ESO. The second Alpha stage proposal was submitted in March 2022. | Completed | The outcome from the Alpha application was published by Ofgem in July 2022. The Virtual Energy System project was unsuccessful. | 06/2021 | This will see the eventual creation of a series of digital twins to cover all sectors of the GB networks. These 'digital twins' can be used to run and test different whole system scenarios and solutions. | National Grid ESO receives Strategic Innovation Fund (SIF) grant to advance development for digitising Great Britain’s energy system ¦ National Grid ESO | No data shared at present; the first stage is about developing a Common Framework for data sharing in a virtual energy system. | N/A | If successful, this innovation project would have seen the creation of a GB Virtual Energy System, which will allow for better cross-sector simulations to inform and accelerate the pace of change in the industry. | Would have allowed SEPD to investigate a wider range of scenarios and potential solutions when planning network interventions. | Project was deemed ineligible for Alpha funding. Potentially reconsider for future SIF rounds if appropriate. | It is important for SEPD to be involved to ensure DNOs' views and requirements are properly considered in developing the solution. This will also ensure future work aligns with SEPD's work.
| SEPD/003 | SEPD | Element Energy, Transport Scotland and Visit Scotland, SHEPD, Isle of Wight Council, IoW Port and Red Funnel Ferries | NIA project (E-Tourism) to investigate the impact on the distribution network from high volumes of visitor driven EVs during the tourist season. Initially focused on the North of Scotland, the second stage of the project considers the impact on the Isle of Wight. | Completed | Project completed in 2022, completing both the studies on Northern Scotland and the Isle of Wight, and completing an additional assessment of two use cases on the Isle of Wight and the possible alternative solutions which could be utilised by Local Authorities/tourism or site operators to help minimise impacts from grid constraints when trying to install EV charging at those sites. | 07/2019 | To deepen understanding of peak demands resulting from tourist-driven Electric Vehicles, and potential for alternative solutions to be utilised by Local Authorities or tourism/site operators to help minimise impacts from grid constraints when trying to install EV charging at those sites. | https://ssen-innovation.co.uk/nia-projects/nia-ssen-0038-e-tourism/ | Used DFES, SSEN Distribution asset data and data from tourism operators along with insights from the Local Authorities. | N/A | Understanding potential issues where seasonal tourism may create new peaks in electricity demand will help both SEPD and the tourism sector develop their plans for electrification of transport. | The project will help DNOs to better predict seasonal tourist peaks. | None. All activities complete. | To further understand the impacts of new - and variable - loads on our network and factor these into our future plans.
| SEPD/004 | SEPD | Local Authorities, Derryherk, Advanced Infrastructure, Arup, Regen, WSP, DESNZ | RESOP is focused on data sharing between Utilities and Local Councils to help with optimal placement of LCTs and develop LAEP/LHEES. | In progress | RESOP has entered its second stage. Launch of the Local Energy Net Zero Accelerator (LENZA) in October 2023 as the software platform for Phase 2 of the RESOP Project. Beginning to onboard more local authorities to the platform (SEPD/026). | 10/2023 | Coordination between local council plans and utilities utilising state of the art data tools enables us to reach net zero goals in a timely cost-effective manner. | https://smarter.energynetworks.org/search-results/?dateType=start&query=RESOP&sort= https://www.ssen.co.uk/our-services/tools-and-maps/lenza/ | EO GIS & CIM / LTDS / Network Development Plan / Authorised Capacity / Network Phase Information / NeRDA substation monitoring data / Network Rating & Loading Information. | https://www.ssen.co.uk/our-services/network-capacity-information/ https://www.ssen.co.uk/our-services/tools-and-maps/ | If successful the project will lead to improved co-ordination and cooperation between local councils and Utilities. Improved ability for local councils to plan energy related projects. | If successful the project will lead to: Reduction in the number of connection requests Increase in the number of successful connection requests Improved visibility to short and long term investment plans of local councils. | The next stage is for local councils to start trialling the tool used in the RESOP project and provide feedback on its efficiency. If the project is successful the next stage start thinking about business as usual implementation. | If successful we would transfer the tools used in this project (or similar tools) into BaU. This is essential for us to assist local councils deliver ambitious net zero climate goals on time and within budget.
| SEPD/005 | SEPD | OZEV, Ofgem, Arup, ENA (and other DNOs) | RCF is the Government's £950 million fund to future-proof electrical capacity at motorway and major A road service areas to prepare for mass EV uptake. Working with multiple partners, the ambition is to have 6 ultra-rapid EV chargers (150kW+) at every Motorway Service Area (MSA) by 2023. | In progress | Continuing to hold bilateral discussions with OZEV to progress delivery of the RCF. Any information including; agendas, notes, minutes and slide packs is confidential and SSEN Distribution are prevented from making available. | 11/2020 | Project spans transport and energy requirements, with the potential for transmission-level impacts as well as distribution level. | https://www.gov.uk/guidance/rapid-charging-fund | Capacity information of networks, indicative timescales for reinforcements, etc. Information on SSEN Distribution's flexible connections (current and in development) and the ENA G100 update. | N/A | Seeking to enable local and national Governments to advance transport decarbonisation plans. | Potentially significant increase in capacity requirements, which will need to be met through flexibility services or network investment. | To organise and hold Connection Surgeries with all MSA Operators to progress the RCF delivery. | All DNOs are expected to facilitate what is seen as a huge enabler for the nation to decarbonise transport.
| SEPD/006 | SEPD | ElectraLink, CrowdCharge, UKPN, EIC | Skyline is a NIA project focused on establishing data sharing agreements with companies involved in the leasing, sale or installation of EVs and EV chargers. The aim is to give DNOs greater visibility of customer enquiries and/or orders to facilitate more proactive network planning in response to EVs. | Completed | Project closed in 2022, after successfully demonstrating ability for parties involved in automotive or charge point industries to share data with DNOs earlier than a connection application would. Now assessing a proposal to move the service into BAU- engaging other DNOs via ENA to assess appetite for a BAU service. | 09/2020 | To enable proactive investment in networks (at all voltage levels) in response to EVs and contribute to effective delivery of local and national decarbonisation projects. | https://smarter.energynetworks.org/projects/nia_ssen_0048/ | Restricted sharing of location information, dates and types of activity (enquiry or order) and whether EV charger or EV. | N/A | Extremely positive. More timely delivery of network upgrades in response to EVs. | Positive. Facilitates strategic investment in response to volume information and expected dates of connection. | Engage other DNOs via ENA to assess the proposal to move the service into BAU. | To promote strategic investment and further enable LCT uptake.
| SEPD/007 | SEPD | NGET & the ESO | Following numerous technical discussions and meetings between NGET and SSEN Distribution System Planning teams, SSEN Distribution submitted a Modification Application to NGET for the installation of a third 400/132kV 240MVA SGT and supplementary equipment (132kV components, metering system etc) at Fawley GSP. This proposal was proven to be most economic, efficient and coordinated solution for resolving the issues and limitations in the Fawley group. | Completed | Third Fawley SGT transformer rated at 240MVA has been energised and is in operation. | 04/2018 | Working in collaboration with NGET to undertake efficient system reinforcement work in the group. | N/A | Reports and presentations. | N/A | The project has shown that collaborating with NGET and the ESO can improve working relationships, management of works and deliver cost efficient solutions for developing the system at the appropriate level. | The solutions will provide a cost effective approach to connect additional customer in the Fawley group. | Use the learnings from this project to inform and enhance future projects that have similar interactions with NGET at our sites.. | Supports close working relationships to drive efficiencies that have a positive impact for network customers.
| SEPD/008 | SEPD | NGET & the ESO | Rationalisation of the shared substation areas containing NGET’s Willesden 275/66 kV GSP and SSEN Distribution's Canal Bank 22/6.6 kV and Canal Bank 66/11 kV substations. The existing Canal Bank 22/6.6 kV substation has asset condition related (poor asset health) and site location issues while Canal Bank 66/11 kV substation has load related issues (no spare capacity). | In progress | Construction is currently underway and forecast completion is summer 2024. Second transformer has been energised. | 09/2018 | Working in collaboration with NGET to undertake works at Canal Bank to co-ordinate replacement activities, re-arrange the site and manage outages. | N/A | Reports, presentations and work instructions. | N/A | The project has shown that collaborating with NGET and the ESO can improve working relationships, management of works and deliver a cost efficient project. | The collaboration has improved the layout and space on site whilst driving cost efficiencies by co-ordinating resource activities. | Use the learnings from this project to inform and enhance future projects that have similar interactions with NGET at our sites. | Supports close working relationships to drive efficiencies that have a positive impact for network customers.
| SEPD/009 | SEPD | Regen, local authorities, large solar PV and battery storage project developers, ITM Power, representatives from European Marine Energy Centre (as based in Orkney or Shetland), the ESO, ENA | The DFES analysis provides scenario projections for changes in generation (low carbon and conventional), demand and storage technologies and their potential impact on the distribution network. Whilst the DFES uses the ESO's four national energy scenarios, its projections are heavily influenced by input from local and regional stakeholders. | Completed Annually | Currently preparing data and carrying out engagement with a wide variety of stakeholders for the next DFES publication in early 2024. | 07/2021 | The outputs of the DFES are used to determine the potential impacts on the distribution network and its potential requirements for flexibility services and investment. It also offers stakeholders, such as local authorities, visibility of potential constraints and opportunities to inform their energy, transport and development plans. | Smart and local benefits for our communities - SSEN | All data from the DFES studies is publicly available. The underlying data is available on request and we often produce tailored versions for local authorities as part of our local area energy plan engagement. | The DFES is available in SSEN's Open Data Portal. | The DFES support whole energy system and long-term planning conversations between networks and regional bodies. | We are working to anticipate the changing needs of network users and ensure our networks adapt and meet these needs. The work that Regen undertakes as part of the DFES is key to this in supporting informed decision making, which enables timely and cost-effective network management. | DFES studies will continue to be produced annually and will form the basis of our network development plans. | The DFES work has been key in informing our Business Plan for the next five year price control period (April 2023-March 2028), is an intrinsic part of our Local Area Energy Plans that we are building with Local Authorities and our future investment strategy to meet net zero ambitions in our licence area.
| SEPD/010 | SEPD | the ESO, NGED, Octopus Element Energy, OHME technologies, Centre for Net Zero. | This is an Alpha Stage SIF project involving multiple parties exploring the potential for domestic flexibility services. CrowdFlex explores how domestic flexibility can be used in grid operations to help align demand to generation, improve coordination across the network, reduce stress on the system, while empowering consumers to be active players through new tariffs and incentives. | In progress | SEPD are a partner in the successful Alpha project which closed in March 2023. The Beta application was approved by Ofgem in July 23. Beta project commenced in October 2023 and partners are preparing for the first round of trials summer 2024. | 05/2021 | This involves multiple industry stakeholders to develop a broad-based approach to the complex issue of domestic flexibility. The project scope has also expanded to include issues in SHEPD area including considerations around Load Managed Areas. | Crowdflex ¦ ESO (nationalgrideso.com) | SSEN Distribution have shared some initial network data relating to Load Managed Areas. SEPD role will involve detailed design of trials etc. as we move through to the demonstration phase. | N/A | Domestic Flex has the potential to provide benefits for both consumers and licensees, if an appropriate route to market can be developed. | By increasing the potential flexibility market, Domestic Flex has the potential to reduce our costs in procuring flexibility to meet customers' needs. | Large scale trials in summer 2024 to test model and prepare for winter trials. | This builds on earlier innovation work delivered collaboratively by SEPD and the ESO, with the ultimate objective being to establish domestic flexibility as a reliable resource for network management.
| SEPD/011 | SEPD | Disabled Motoring UK, Energy Systems Catapult | NIA project (Equal Electric Vehicles) investigating barriers and enablers for drivers with disabilities / vulnerabilities to be able to make the switch to EVs. | Completed | Attempting to secure funding to continue assessing elements of customer resilience. | 10/2020 | Brings together DNOs, the automotive industry, local authorities and national Government to consider the holistic measures needed to facilitate inclusive and accessible decarbonisation of transport. | https://smarter.energynetworks.org/projects/nia_ssen_0049/ | Reports and presentations. | Equal Electric Vehicles ¦ ENA Innovation Portal (energynetworks.org) | Project has stimulated multiple projects and initiatives highlighting the need for accessible EV charging standards. The Government has subsequently produced a consultation and planned new standards using Equal EV's findings. | Further enables SSEN Distribution's fair transition to a smarter energy system, including better support for PSR customers. | To progress several concepts linked to supporting vulnerable customers in outages, most likely via new innovation projects. | Supports inclusivity and builds upon the public support for accessibility.
| SEPD/013 | SEPD | Local authorities (District, Borough, City, Unitary, and County Councils) across SEPD, the Greater South East and South West Net Zero Hubs, Energy Saving Trust, Energy Systems Catapult, Regen, other regional and local organisations | Constructive engagement with local authorities across SEPD and other key stakeholders who have a significant impact on our network. This engagement is aimed at supporting the development of local area energy plans (LAEPs) and wider strategic energy planning. | In progress | SSEN's DSO has a new team of Net Zero Engagement Specialists who are leading on engagement and collaboration for strategic energy planning across our two licence areas. Whole system activities thus far include the rollout of LENZA (SEPD/026) and LAEP Workshops held with multiple Local Authorities across the SEPD licence area in March 2024; these workshops were two, full-day events, one in Bournemouth and one in Reading for our local authority partners to discuss the importance of strategic energy planning, what it could look like, and how local authorities, their wider stakeholders and SSEN could work collaboratively to enable strategic energy plans that enable SSEN to make informed decisions on network reinforcement. Non-local authority partners also attended, including the ESO, university, and NHS organisations. | 01/2023 | Engaging with local authorities and supporting preparation of Local Area Energy Plans is a key whole system activity to enable achievement of net-zero ambitions through stakeholder informed strategic network investment. | https://www.ssen.co.uk/about-ssen/dso/whole-system/local-area-energy-planning/ https://ssen.engage-360.co.uk/events/3957?q=2022%7cOrL6u9MNErmjKwozGMmxyfrEFpl7AZsPzb9cw2WvjtKaEwb0VAzKdS9oHhRdGwPd | Engagement includes signposting to key datasets, such as geospatial and network capacity data, published by SSEN and data sharing via LENZA. During the LAEP workshops, Regen gave a high level preview of the latest (2023) DFES report which is now published and available on our website. We (SSEN) also demonstrated sources of data on our Open Data Portal and how to gain insights from them. | N/A | This engagement facilitates improved coordination and collaboration while accelerating strategic energy planning. The workshop events had a positive impact as they have helped bring a number of stakeholders together to consider the benefits and imperative nature of whole system planning. | Building meaningful relationships with key regional and local stakeholders improves SSEN Distribution's visibility of longer-term energy needs of local communities served by our network, which strengthens our strategic network development. | Continue to build strong working relationships with local authorities and other key organisations in the strategic energy planning space. Consider the responses and feedback of workshop delegates to understand how we as a Net Zero Engagement Specialist team can operate to support our local authorities in the best way possible. | To ensure working relationships with local authorities and wider stakeholders continue to grow and become increasingly beneficial to all the involved parties.
| SEPD/014 | SEPD | GLA, Arup, West London Alliance, OPDC | Through the GLA, SSEN Distribution are providing data and supporting the development of LAEPs to understand development ambitions, net zero targets and how they impact our distribution network. | In progress | SSEN contributed network data to the Local Energy Asset Representation (LEAR) produced by Arup for the West London Alliance area. | 09/2022 | LAEPs bring multiple inputs from third parties to develop a strategic view of area expansion. This includes electricity, gas, developers, councils etc. | N/A | The data sharing is bi-directional. Network information, such as asset locations, building information (energy performance certificates), reinforcement plans, development plans. | N/A | This work will enable Local Authorities and third parties in the West London area to make informed investment decisions, understand the impact of those investment decisions on utilities, and support the justification for utility investment. | This work is helping inform how SSEN Distribution will engage with other Local Authorities to build meaningful and proactive LAEPSs to facilitate and enable Net Zero ambitions. | Continue to engage, share data and build a plan out to 2050. This will help to ensure that all areas have clear and justified plans that will enable utilities to undertake anticipatory investment. | Continued data and knowledge sharing will improve working relationships, enhance collaborative approaches, drive efficient working practices and enable all parties to evidence future investment requirements.
| SEPD/015 | SEPD | The ESO, NGET, GLA | Long term transmission investment in the GLA area, covering six GSPs, had the potential to reduce customers ability to connect to the distribution network. This collaborative project (West London Electrical Capacity Constraints) aimed to remove barriers for connections, review contracted queue management and determine material thresholds for each GSP. | In progress | SSEN Distribution have introduced a new process as a trial for customers connecting to the GSPs within the GLA area. This will offer customers the ability to stage their connection; connecting within the materiality threshold each year. We are now looking to use this process more widely across our licence areas. In addition we have also developed flexibility services to release additional capacity in the areas. | 07/2022 | This work combines extensive stakeholder engagement with the GLA, the ESO & NGET. SSEN Distribution have also put forward a process to the ENA for approval with all other DNOs. | West London Electrical Capacity Constraints | There is a data sharing agreement in place for some data being shared. Other data being shared is associated with publicly available information; such as Heat Maps, network development plans, GIS network data etc. | Network Capacity Information - SSEN | The process is enabling customers to connect to the network ahead of wider transmission reinforcement and is improving data sharing to inform future investments. | Positive impact that demonstrates that through successful stakeholder engagement, distribution and transmission businesses are able to work collaboratively to remove connection barriers. | SSEN Distribution are having on-going monthly meetings with GLA, NGET and the ESO to ensure that we proactively progress the proposals and are prepared for any future concerns that may arise. | Continued data and knowledge sharing will improve working relationships, enhance collaborative approaches, drive efficient working practices and enable all parties to evidence future investment requirements.
| SEPD/016 | SEPD | Oxford City Council, Oxfordshire County Council. Low Carbon Hub, University of Oxford | New SIF application submitted in November 2022 - LEO-N, which will develop the outcomes from the previous project LEO. The project will focus on how to scale the delivery of the net zero transition at a local level and the governance arrangements to support this. The project was successful in its Alpha stage application and the stage has concluded in April 2024. | In progress | Alpha stage completed. | 05/2022 | The project looks to coordinate a range of local actors including local authorities, community groups and DNOs to scale the net zero transition in Oxford and Oxfordshire. The project will develop customer journeys for Future fit and will identify options for local governance arrangements to better coordinate the transition. | LEO-N ¦ SSEN Innovation (ssen-innovation.co.uk) | Still to be determined but potentially will include DFES and LV Monitoring Data. | N/A | Acceleration of net zero transition in Oxfordshire by better coordination between community groups, local authorities and DNOs. | This should allow DNOS to make better informed decisions on future network investment especially at a local level. | Start the Beta stage of the project. | Project will be developed following the process outlined in SIF Governance document.
| SEPD/017 | SEPD | ENA, DSOs, the ESO & TOs | As part of Open Networks through the ENA, all DSOs, TOs and the the ESO have agreed to collaborate and deliver business change across multiple areas; including Planning & Network Development, Network Operation and Market Development. | In progress | SSEN currently chair the Planning and Network Development workstream and lead the Settlement technical working group. We also fully engage on all other workstreams and technical working groups. | 09/2022 | To deliver all of the outcomes within the ENA launch documents all distribution and transmission businesses are required to work together to enact business change across networks to improve collaboration, cooperation and deliver common practices that will benefit stakeholders. | open-networks-2023-launch-document-(jan-2023).pdf (energynetworks.org) | There is a data sharing agreement in place for some data being shared between parties within the ENA. There will be publicly available information as projects within Open Networks progress and conclude. | Open Networks: developing the smart grid - Energy Networks Association | The work is driving a common approach across distribution and transmission businesses to deliver value to stakeholders and coordinate thinking. | SEPD have direct influence on decision being made and are responsible for ensuring that agreed approaches are implemented within the business. | Continue to proactively engage in all the products, workstreams and steering group to ensure that the commitments made in the launch document are being delivered. | As a business we have committed ourselves to collaborating across all activities, putting forward our views and incorporating decisions into our business. As such, we must proactively engage across all products, workstreams and the steering group.
| SEPD/019 | SEPD | International Community for Local Smart Grids (ICLSG), CORENA, WEL Networks, TEPCO Power Grid, Low Carbon Hub, University of Oxford | SSEN Distribution co-founded the ICLSG, which is a knowledge-sharing partnership founded to accelerate a fair, resilient and local transition to net zero. Local smart grids will play an important role in achieving both international targets and local ambition, whilst maintaining network resilience. | Completed | International webinars held for Global North and Global South, each attended by approx. 100 stakeholders from ten countries, to discuss network resilience in a decarbonising world (November 2022); first research project (into network resilience) completed, second research project (challenges and opportunities of distributed smart energy assets in progress); deep dive into the role of data just beginning. Bilateral held between SSEN and TEPCO to share learnings on support for vulnerable customers (January 2023). Monthly meetings allow all partners to share learnings from innovation projects (e.g. ESB's Dingle project in Ireland, shared March 2023). We are expanding it to integrate more closely with the activities of CIRED to leverage a larger and more international network building on the success of ICLSG. | 11/2021 | Engaging with a number of grid operators and stakeholders across the globe to share learnings about the challenges and opportunities of the DSO transition. | International Community for Local Smart Grids (communitysmartgrids.org) | SSEN feeds into research which is being conducted by the University of Oxford; those reports are shared privately with partners and then released publicly three months later. Partner meetings when learnings from specific projects are shared are private, as are the conversations during bilateral meetings between DSOs. | Projects - International Community for Local Smart Grids (communitysmartgrids.org) | Allows understanding of innovative ways for integration of local smart grid technology and how DSOs can engage most effectively with local communities, to support their transition. | Trials across the SEPD licence area provide a better understanding of network use at a local level, for example learnings from Project LEO. Results from other DNOs worldwide will provide innovative solutions to the challenges of connecting local smart grids. | Continue to engage and share experience with collaborators in the ICLSG. | Sharing experience with global partners will help provide valuable insight into the challenges faced when integrating local smart grids. Overcoming these challenges will help SSEN Distribution to accelerate towards, and enable local areas to participate in, a net zero world.
| SEPD/020 | SEPD | All 6 DNOs and Ofgem. | The continued development of the CNAIM to support RIIO-ED2 and RIIO-ED3. Collaboration on the changes proposed, analysis carried out and agreement on the changes made. | In progress | Looking to engage with ENA and other bodies (still at early stages of the scope of works) | 01/2019 for RIIO-ED2; 02/2023 for RIIO-ED3 | Engagement in the Cross Sector Working group in discussions around Condition related modelling methodology. | N/A | Asset and Fault Data shared between DNO's in the development of the Methodology. Sharing of Asset data to identify common data points concerning non-NARM asset types. | N/A | Enables a more efficient network. | Positive impact in helping to develop a meaningful Common Modelling to support investment decision making and reporting to Ofgem. | Waiting for OFGEM decision. | Agreement needed from all DNOs and OFGEM.
| SEPD/021 | SEPD | Geospatial Commission | The NUAR project provides GIS Networks data to support Geospatial Commission launch of product. | Completed | Data provided for launch, now in the updating of data on regular basis phase | 04/2023 | Project involving many utilities & statutory undertakers who own assets. | National Underground Assets Register (NUAR) | GIS network shapefiles. | N/A | The project enables access to a single source of network records of asset owners involved, to be used by statutory undertakers & helping reduce cable damages. | Positive reputational impact of being involved at launch. | Update process | Clear update process will ensure register reflects current positions of network assets.
| SEPD/022 | SEPD | ENA, DSOs, the ESO, TOs, DESNZ & Ofgem | Through the ENA's Strategic Connections Group, we are helping to make rapid changes to improve how customers connect to the grid at distribution level. Implementing 'quick win' changes to the connection process for customers seeking connection to the distribution networks in three priority areas: (i) Reforming the distribution network connections que; (ii) Changing how Transmission & Distribution coordinate connections; (iii) Greater flexibility for storage customers connecting into the distribution network; (iv) Distribution forecasted transmission capacity; (v) Transmission charging reform. | In progress | Ongoing input into working groups. | 02/2023 | Quick win changes in the three priority areas will help manage the distribution connection queue and accelerate connection of customers to the network. | Improving and accelerating customer connections – Energy Networks Association (ENA) https://www.ssen.co.uk/about-ssen/our-works/technical-limits-at-gsps/ | Data has been shared by DNOs to input inform potential solutions in the 3 priority areas. | N/A | Solutions to the key priority areas will resolve some of the significant queue delays faced by customers. | Key to enabling customer connection to the network, reduces the number of customer complaints. | Continued participation in the Strategic Connections Group to achieve the 'quick wins' in the 3 priority areas. | Solutions will deliver benefits to the Whole System.
| SEPD/023 | SEPD | ENA, DSOs, relevant UK and GB Trade Associations, specialist external consultants, relevant manufacturers, and suppliers | Participate in various ENA working groups to develop new and update existing ERECs and EREPs, the recommendations and reports that the working group produces. These are typically focused on best practice or guidance information. Application of the EREC documents that support Distribution Code is mandatory. | In progress | Ongoing participation in working groups. | N/A | ERECs & EREPs are kept up to date so that they remain relevant to the needs of the distribution network and its customers. | Standards and guidance – Energy Networks Association (ENA) | ERECs & EREPs are published on the energy networks association document catalogue. | Standards and guidance – Energy Networks Association (ENA) | Ensures that the industry recommendations remain relevant and up to date. | Assists the licensee in complying with relevant statutory obligations as set out in our licence conditions. | SSEN to maintain support to the current and future areas of work. | Continues to assist with compliance with statutory obligations.
| SEPD/024 | SEPD | The ESO, TOs & DSOs | Connection and Use of System Code (CUSC) is the contractual framework for connecting to and using the National Electricity Transmission System, Modification proposals (CMP) are submitted by users to change these codes. | In progress | Continue to actively participate in modification proposals. | 09/2019 | Due to the nature of CUSC, modification proposals are relevant to the whole electricity system. | Connection and Use of System Code (CUSC) ¦ ESO (nationalgrideso.com) | N/A | N/A | Ensures more efficient operation of the network. | Ensures the necessary contractual relationships are best for the parties involved. | SSEN to remain engaged with CMPs and contributing proposals where there is potential benefit. | Future CMPs will provide added value to the Whole Electricity System.
| SEPD/025 | SEPD | The ESO, TOs & DSOs | Grid Code working groups member. The grid code sets out the operating procedures and principles governing the relationship between the company and all Users of the National Electricity Transmission System. Various working groups ensure that new requirement and/or adjustments/ continuation of corresponding existing GB requirements align with new codes. For example, workgroup member for GC0139: Enhanced Planning-Data Exchange to Facilitate Whole System. This modification seeks to increase the scope and detail of planning-data exchange between DNOs and the ESO to help facilitate the transition to a smart, flexible energy system by aligning certain data exchange processes, providing greater granularity of data at a wider range of operating conditions. | In progress | Workgroups are ongoing. | 02/2020 | Increases the scope and detail of planning-data exchange between DNOs and the ESO. This will align certain data exchange processes, providing greater granularity of data at a wider range of operating conditions. | GC0139: Enhanced Planning-Data Exchange to Facilitate Whole System Planning ¦ ESO (nationalgrideso.com) | Details of the sub-transmission network. Including details of all Distributed Energy Resource (DER) greater than 1MW connected to the distribution network and their impact on energy flows at extremes for example peak demand, summer minimum, solar-peak/daytime-minimum demand. Proposed to be shared between DSOs and the ESO. | N/A | Facilitates efficient and coordinated planning of both the Transmission system and Distribution Networks. This efficient and coordinated planning will provide benefits to customers in the long term. | This activity will improve SSEN's understanding of the transmission system flows and fault contributions within a variety of demand/generation scenarios. | Maintain attendance to work groups. | Improvements to the grid code will benefit all DNOs and TOs.
| SEPD/026 | SEPD | Advanced Infrastructure Technology Ltd, local authorities | LENZA is a local area energy planning tool developed through Project RESOP, an innovation trial (see SEPD/004). SSEN is rolling out this software platform to local authorities across the SEPD licence area to support planners in reaching their net zero targets through optimal placement of low carbon technologies and scenario planning. | In progress | The LENZA rollout was launched in October 2023, and phased onboarding of local authorities proceeded from there. As of April 2024, LENZA has been made widely available to the local authorities across both SEPD and SHEPD. SSEN DSO's team of Net Zero Engagement Specialists (SEPD/013) is leading on the whole system engagement that supports the LENZA rollout programme. | 10/2023 | The whole system engagement that LENZA facilitates promotes efficient data exchange and strategic collaboration to find optimal solutions for reaching local net zero ambitions. | LENZA - SSEN | Restricted sharing of data within the LENZA platform, which can include network data, council building data, and other datasets relevant to local area energy planning. See SEPD/004. | N/A | Positive; accelerates local authorities' progress toward a local area energy plan and reaching net zero targets on a local scale. | Positive; local area energy plans can serve as a key input to SSEN's strategic investment decisions given the visibility they lend to local development and evolving demands on the network. | Continue onboarding programme and engagement with LENZA users to understand local net zero aspirations and pathways. | Continued engagement is crucial to feed local data and insight into SSEN Distribution's strategic network development.
| SEPD/027 | SEPD | Electricity Northwest, CGI, Origami Energy, Atkins | TRANSITION was an NIC-funded innovation project led by SSEN to explore the role of flexibility markets in the electricity system. TRANSITION worked in close conjunction with Project LEO (SEPD/001), as trials were based in Oxfordshire. The project's aims were to: 1) inform the design requirements of a DSO-facilitated flexibility marketplace and network interface; 2) to develop the roles, responsibilities and rules within the marketplace; and 3) test these requirements through a programme of trials in Oxfordshire. | Completed | Concluded in September 2023. | 09/2018 | TRANSITION involved collaboration with other network operators along with wider industry partners to explore the development of a neutral market facilitator. | https://ssen-transition.com/reports/transition-close-down-report/ | Near Real-time Data Access (NeRDA) and ElectraLink's real time settlement data were utilised in TRANSITION to support operational forecasting. One of TRANSITION's main objectives was to define the data requirements for DSOs to implement a flexibility marketplace. | https://www.ssen.co.uk/our-services/tools-and-maps/near-real-time-data-access-nerda-portal/ | Positive; uncovered key learnings about flexibility marketplaces that will improve electricity system operation for both network operators and their customers. | Positive; provided a host of learning outcomes for SSEN about flexibility marketplaces that are being integrated into BAU and supporting the transition from DNO to DSO. | N/A | N/A
| SEPD/028 | SEPD | NGET & the ESO | SSEN and the the ESO are working on multiple Regional development programmes (RDPs) and TD boundary ANM systems set up to meet new contractual requirements between NGET and SEPD. These RDPs and TD boundary ANM systems were introduced because the amount of DERs connected, and connecting to the distribution networks was believed by the the ESO to be impacting the transmission network. Examples include SWAN and Minety GSP. | In progress | Minety is operationally live as of 10/2023. SWAN is now operationally live as of March 2024. | 05/2017 | Collaboration across electricity transmission and distribution licensees allows for more customers to connect to the distribution network ahead of transmission related reinforcement. | SWANS - SSEN | SSEN and the ESO have established an ICCP. It's a two way datastream with near real time demand and generation data. | N/A | Efficiently maximises benefit from the existing distribution system and reduces the need for a traditional asset augmentation/investment type approach. Provides early access for customers to distribution networks. | Enables growth in terms of use and ability of ANM systems to help meet the growing demands and expectations of our customers. | Continued improvement and use of ANM systems. SSEN will connect more DERs onto the ANM system. | This will support growth in flexibility, dynamic management of our networks, and enables customer connections.
| SEPD/029 | SEPD | The ESO, Frazer Nash Consultancy, NPG | Project CASCADE's overarching aim is to provide the control room with comprehensive insights into GSP sub-network characteristics in near real time, with a particular focus on ANM schemes; their available headroom, ramp-rate and reliability of supply within a given time-horizon. The Discovery phase will define the use cases, system specification and roadmap for BAU deployment while also undertaking a cost-benefit analysis to demonstrate value for money and an optioneering exercise to assure a cost-effective development route is chosen. | In progress | Meetings have been attended and are ongoing. | 02/2024 | Stops conflicts between active network management and flexibility services. | N/A | N/A | N/A | Positive - Improves coordination between ANM and flexibility services to increase network capacity. | Positive - Supports the implementation of primacy rules. | Continued Participation. | N/A
| SEPD/030 | SEPD | CSE & Flex Assure | The HOMEflex project aims to develop the tools to build trust in the domestic flexibility market and support consumers' engagement. A Code of Conduct that flexibility providers can sign up to has been developed through a process of market analysis and stakeholder engagement led by SSEN with Flex Assure. In addition, the CSE has run qualitative research groups of households to discuss their concerns and expectations about flexibility service providers. These insights are now being used by the HOMEflex team to set up a compliance scheme. | In progress | Code of Conduct launched in October 2023 and being used by the ESO in the Demand Flexibility Service (DFS) 2023/24. Compliance scheme being set up. | 06/2022 | Ensures that all flexibility market participants, from the DSO/DNO to the aggregator who acts as a go-between, to the domestic or microbusiness customer, can have confidence in the process and the market. Involvement from both sides required for successful delivery. | Household Or Microbusiness Energy flexibility (HOMEflex) SSEN ¦ SSEN Innovation (ssen-innovation.co.uk) | Methodology, results and insights from engagement. | HOMEflex Qualitative Research Report (ssen-innovation.co.uk) | The HOMEflex project code of conduct should ensure that the consumer protections will keep pace with flexibility market innovation. | Builds customer trust in flexibility market. Leads to increased participation. Promotes best practice within the industry. | Set up compliance scheme and engage with DFS flexibility providers. | Allows launch of compliance scheme to support code of conduct. Understand requirements for next winters DFS. | HOMEflex compliance project. | 03/2024 | New | N/A
| SEPD/031 | SEPD | Imperial College London, The Smith Institute, National Energy Action. | VFES looked to combine academic foresighting, Machine Leaning data and expert evaluation to focus on less resilient area, with consumers who rely more than most on electricity. The aim was to help inform DFES on a customer and community level far better than previously possible. | In progress | Publication in the most recent DFES. | 08/2022 | Allow visibility and future prioritisation of more customers who rely on energy more than most. | https://www.ssen.co.uk/news-views/2024/SSEN-puts-vulnerable-customers-at-heart-of-future-energy-strategy/ https://smarter.energynetworks.org/projects/nia_ssen_0063/ | Data from forecasting models. | N/A | Helping create an equitable net zero transition. | Better visibility of less resilient communities, allowing SSEN to include in DFES forecasts which allow for better network reinforcement decisions. | Embed VFES into more components of the DFES model. Also, help inform the ED3 business plans. | Promote a just transition that safeguards vulnerable customers and communities.
| SEPD/032 | SEPD | SGN, Utility Week, local authorities | SSEN, in partnership with SGN, has hosted a series of roundtable discussions with local authorities exploring different themes around local area energy planning: decarbonisation of heat, decarbonisation of transport, connections and capacity, and funding the Just Transition. In addition, Utility Week is undertaking market research with local authorities across the UK (across several DNO licence areas) to further understand some of the challenges. This work culminates in a face-to-face event in London. | Completed | 4 virtual and 1 in person roundtables have been held, with write-ups finalised and follow-up interviews completed. High-level market research has also been undertaken. Utility week has published a findings report and insights data has been produced. | 07/2023 | Coordination with other energy network operators and wider industry stakeholders to understand opportunities and challenges around local area energy planning. | N/A | Survey responses to the Utility Week market research. Restricted sharing. | N/A | Positive; better understanding of the barriers to local area energy planning. | Positive; valuable insight from customers and stakeholders will ensure we offer support and resources that are fit for purpose. | Disseminate learnings from the final report both internally and externally. Need to deliberate on best ways to take findings forward into our stakeholder engagement and strategic investment workstreams. | Ensure we use the findings from this work to improve our service for stakeholders and customers.
| SEPD/033 | SEPD | The ESO, Other DSOs, Commercial Businesses, Local Authorities, Battery Storage Owners, Large Energy Users, Distributed Generation Customers, Aggregators, Domestic Customers | Our DSO Accelerator Program delivered a variety of engagement sessions with stakeholders in line with 4 strategic priorities; forecasting and planning future needs, developing an inclusive flexibility marketplace, delivering network flexibility at scale, driving transparency and coordination. Our outputs included consultation on and creating our DNOA Methodology, ODM, Data Roadmap and Flexibility Market Platform | Completed | Our DSO Accelerator delivered on key outputs that now will need to continue to be delivered as part of DSO business as usual processes. | 08/2023 | Coordination and cooperation with stakeholders to ensure the DSO can meet future needs of a net zero grid. | https://www.ssen.co.uk/about-ssen/dso/publications-and-reports/ | Methodologies were shared, reports shared in draft for consultation and published on the SSEN website. | https://www.ssen.co.uk/about-ssen/dso/publications-and-reports/ | Positive, increases DSO capability leading to a more efficient whole system. | Positive, increases DSO capability. | Disseminate learnings from the final report both internally and externally. Need to deliberate on best ways to take findings forward into our stakeholder engagement and strategic investment workstreams. | To ensure SSEN is an effective DSO.
| SEPD/034 | SEPD | LEMA, Gemserv, The Traxis Group | The LEMA Ltd is a company founded by Gemserv & The Traxis Group. LEMA is needed to bring together broad market interests in how LES can play a significant role in mitigating Grid Constraints for DNOs and National Grid. | In progress | Forming a common interest group. Supporting networks, data, and platform. | 07/2023 | Investigating how new build housing can be enabled particularly with low carbon technology. | Local Energy Markets Alliance - Commercial Market Solutions ¦ Local Energy Markets Alliance (LEMA) | N/A | N/A | Enables accelerated uptake of low carbon technologies breaking down the technical and commercial barriers. | Accelerate the connection of low carbon connections. | Form the common interest group and support on networks, data, and platform. | Providing technical support to the LEMA.
| SEPD/036 | SEPD | The ESO, Aurora Energy Research, Energy Systems Catapult, Modo Energy, National Gas, National Grid Ventures, SGN, University of Oxford | Participation in the the ESO's VES Use Cases Advisory Group. The external advisory groups for the VES programme provide insights and guidance to inform and shape project activities and development work. | In progress | Ongoing input into advisory groups. | 03/2023 | The ambition of the VES programme is to enable the creation of an ecosystem of connected digital twins of the entire energy system of Great Britain. | www.nationalgrideso.com/future-energy/virtual-energy-system | N/A | N/A | This ecosystem of connected digital twins will enable the secure and resilient sharing of energy data across organisational and sector boundaries. This sharing of data will facilitate more complex scenario modelling to deliver optimal whole-system decision making, resulting in better outcomes for society, the economy, and environment by balancing the needs of users, electricity and gas systems and other sectors. | positive - insight into wider perspectives and thinking on the future development and integration of energy systems. | Continued participation. | To inform the pilot project that SSEN Distribution is contributing towards. | Pilot project is now being co-developed between the ESO, NGET, and SSEN Transmission. | N/A | New | Participation in the ESO's Virtual Energy System Use Cases Advisory Group.
| SEPD/037 | SEPD | All 6 DNOs, the ESO, WSP. | Project Commander Identifies and defines alternative the ESO/DSO coordination schemes for accessing and managing DERs with respect to their qualification, procurement, dispatch and settlement. In particular, the roles and responsibilities of the key actors involved, their high-level interfaces across different timescales and information exchanges as well as key market arrangements to facilitate the process. Quantify and assess the techno-economic feasibility of alternative the ESO/DSO coordination schemes for accessing and managing DERs for service provision at operational timescales Develop an engineering-based roadmap and recommendations for the practical implementation of the preferred the ESO/DSO coordination scheme. | In progress | Series of workshops have taken place. | 10/2023 | Improved coordination by information sharing between DNOs and ESO by establishing channels of communication. | N/A | N/A | N/A | Improved coordination between DNOs and the ESO. Help to better inform and understand primacy rules for the ENA Open Networks project. | Help inform all coordination for data sharing activities. | Report on workshops to be produced. | Inform DNOs and the ESO about the outcome of the report.
| SEPD/038 | SEPD | The ESO | PODE trying to build a better cross industry view of potential outage plans across both the Transmission and Distribution networks and how we can get a better wider organisation view of that and share the associated data so that all parties can make more informed and data driven decisions around outage plans to become more joined up and effective. | In progress | Early stages. The project has been initiated and meeting has taken place with the ESO. | 02/2024 | Means whole systems outage planning will be possible. | N/A | N/A | N/A | Coordinated outage planning activities leading to customers being less effected. | Better coordination of outage planning. | The ESO will decide on how to move the project forward. | N/A
| SEPD/039 | SEPD | The ESO, Capgemini | The DER Visibility project aims to increase the visibility of DERs and CERs for electricity system and network operators. | In progress | 6 online workshops and 1 in person workshop have taken place. | 10/2023 | Due to this visibility operators will have the ability to improve the operation of the whole-energy system. | N/A | N/A | N/A | Improves the operation of the whole- energy system | More efficient operation of network. Better flexibility market access and liquidity, more informed decision making. | Impact assessment of DERs. | Gain better understanding DERs impact on the electricity network.
| SEPD/040 | SEPD | ENA, Water UK, All 6 DNOs, Water Companies in England. | PSR Data Sharing Project. This group has been set up to progress data sharing between water companies, DNO's & energy suppliers. There has been a phased approach where all DNO's changed the legal basis for processing PSR data from explicit consent to legitimate interest and substantial public interest on April 23. Two-way data-sharing agreements were put in place with water companies in England and Wales. This has ensured more customers are safeguarded. The project continues into another phase where we will aim to share with energy suppliers and look at an industry solution where all data can be shared universally. | In progress | The ENA have just employed a project manager to co-ordinate this with DNO's. | N/A | Collaboration and coordination across utilities to ensure the safeguarding of customer data. | https://utilityweek.co.uk/shared-psr-to-go-live-at-end-of-march/ | Special Category Data related to the Priority Service Register in the format of industry needs codes, name, address, contact telephone number, nominated contact, nominated contact telephone number. Shared via secure extranet sites on encrypted files. | N/A | Positive as ensures that customers are safeguarded. | Positive, shows SSEN and all DNO's have listened to the feedback from ICO to change legal basis to be able to two way data share with water companies, SSEN began two way data share with 8 water companies where we had only shared data 1 way with 5 water companies previously again expanding the work we do and safeguarding customers. | Next stage is looking to have all DNO's and water companies working to same format and then an industry solution. | To better protect vulnerable customers.
| SEPD/041 | SEPD | ENA, All 6 DNOs, GDN's, Energy Suppliers, | ENA Safeguarding Customer Working Group was set up to facilitate how members of the ENA can safeguard vulnerable customers. The group was fundamental in the set-up of the PSR and ensuring DNO's & energy suppliers could two-way data share. The group ensured collaboration and working together for all members of the ENA. The group has just been disbanded following GDN's leaving the ENA. | Completed | Main conversations will now go through the ENA Customer Service & Vulnerability Working Group. | N/A | Collaboration and coordination across utilities to ensure the safeguarding of network customers. | N/A | The data was topical depending on what was happening eg Storms, Rota Load Disconnections, PSTN Switch Off - from here we could have open discussions or then work in sub groups of some topics. | N/A | Positive as ensures that customers are safeguarded. | Positive, as SSEN Distribution have better ability to protect customers. | Some matters will now go through ENA CSV however this will not include GDN's, GDN's will engage with DNO's independently. | Seen as a more effective solution.
| SEPD/042 | SEPD | EIC, All 6 DNOs | Customer Services & Future Networks worked together to look at projects which could impact customers, a concern was the PSTN switch-off. The move from copper-based analogue lines to digital lines has the impact that during a power cut customers will be unable to use their phone. As we look after PSR customers this worried us and the impacts to them so we have a collaboration project with the EIC and other DNO's are looking to install emergency phone line in communities, allowing customers to contact their DNO in the event of an emergency. | In progress | N/A | N/A | Collaboration and coordination with network operators to ensure that customers are safe in the event of a network outage. | https://www.ukeic.com/opportunities/keeping-communications-open-during-hv-faults | There have been proposals by inventors for a solution shared. | N/A | Positive, ensures customers are safe in the event of a network outage. | SSEN are leading this collaboration which is positive, this shows our commitment to a serious issue which our customers and ourselves have concerns about. | The project is currently getting confirmation on costings etc. | Ensure project is effective. | There is also a sub working group which handle this topic too and we look at the impacts it has on customer. | 04/2024 | Improving | N/A
| SEPD/043 | SEPD | Affinity Water, Bournemouth Water, Bristol Water, Portsmouth Water, South East Water, Southern Water, Thames Water, Wessex Water, SGN, WWU, NHS Highland Telecare, Home Energy Scotland | SSEN have data-sharing agreements in place with several partners who have recognised vulnerability and share this onwards with SSEN to safeguard them and benefit from the PSR. There are 8 water companies in England, Affinity Water, Bournemouth Water, Bristol Water, Portsmouth Water, South East Water, Southern Water, Thames Water & Wessex Water. Data is also between from SGN, WWU, NHS Highland Telecare, Home Energy Scotland. | In progress | N/A | N/A | Collaboration and coordination across utilities to ensure the safeguarding of customer data. | Previous SECV submissions this has been highlighted. | Data related to PSR, name, address, phone number etc | N/A | Positive, as the data that can be used for the more efficient running of the network is carefully safeguarded. | Positive as we are working collaboratively with other partners | Continued data sharing with these partners and looking for more partners to continue this with. | Help more customers.
| SEPD/044 | SEPD | Any third party e.g. City Council, local authorities, innovation groups | The Open Data project setup to enable consumption data to be collected by SSEN Distribution from smart meters. This has been defined by Ofgem as open data, which requires the data to be made available to any third party wishing to access the data through an open data portal | Completed | Ongoing collection of data has been switched on and is being fed through to the open data portal which is available externally. | 09/2023 | Ensures better utilisation of smart meter data to external stakeholders resulting in overall whole electricity system benefits. | https://data.ssen.co.uk/ | Consumption data smart meters aggregated to LV feeder level. | https://data.ssen.co.uk/ | Positive impact for both distribution and external stakeholders to drive benefit realisation through more informed decision making, innovation and net zero commitments. | Positive impact on SSEN and customers as this provides an insight into LV demand consumption previously unavailable which can improve multiple areas of the business and customers | Continue with the collection of smart meter consumption data and make this readily available externally | As part of the introduction of consumption data, SSEN must make this data open and accessible to third parties.
| SEPD/045 | SEPD | Electricity Suppliers, Smart Meter Implementation Programme | A pilot study as part of an industry-wide initiative, driven by the RECCo looking into electricity theft. Through smart metering alerts and data received by suppliers and DNO's, can this data be used to highlight energy theft. | In progress | Completing internal DPIA and preparing to receive data from RECCo to check on what data we had received. | 08/2023 | To enable identification of energy theft through smart meters, brining further smart meter benefits through utilisation of the data. | N/A | Outage, aggregated consumption data, tamper alerts and voltage data | N/A | Positive impact for both distribution and external stakeholders to drive benefit realisation through a greater understanding of meter tampering and energy theft. | Positive impact by enhanced decision-making and timely awareness. Potential to highlight customer tampering where previously unknown. | Continue with pilot study to help coordinate and provide support | These activities support the overall benefit realisation activities associated with smart metering
| SEPD/046 | SEPD | Electricity Suppliers, Meter Operators, DNOs | Coordination activities and regular meetings between the SSEN smart metering and LCT teams to produce data that highlights areas where voltages may be out of limits. | In progress | Producing ongoing reporting which can be utilised by internal teams/users. | 12/2023 | Utilisation of smart metering data to identify areas of concern and to address potential voltage issues arising from LCT installations. | N/A | Voltage alerts received from smart meters | N/A | Positive - broad assessment of all networks that are out of tolerance related to LCT installations, resulting in the more effective decision making. | Positive. Supported efficient decision-making and information. Customers quality of supply. | Continue to build reporting facility and request feedback before full productionisation of reporting. | These activities support the overall benefit realisation activities associated with smart metering.
| SEPD/047 | SEPD | Electricity Suppliers, Meter Operators, Alternative HAN Company, DNOs | A pilot study as part of an industry-wide initiative, driven by the Alternative HAN Company to facilitate the installation of smart metering equipment within crowded meter rooms. | Completed | The CMRC process has been given final approval to be carried out to aid the smart meter roll-out. | 09/2023 | Allows for wider installation completion, bringing smart meter benefits to more customers, and progressing towards a complete smart meter roll-out. | N/A | Data will be sent to SSEN by the Alt HAN Co- this includes Resolution Plans and Schematics for SSEN sign off, alongside customer service alteration applications. | N/A | A positive impact for Distribution and for customers, allowing a wealth of new smart metering datapoints as well as smart metering benefits conferred to customers. | Positive impact on SSEN and customers as this provides visibility into LV demand consumption that was previously unavailable. This can help deliver insights, data and improvements to multiple areas of the business and confer further benefits to our customers. | Maintain alignment with Alt HAN Co to ensure resolution plans can be completed successfully. | The crowded meter room process is now live within industry therefore SSEN Distribution will benefit from keeping aligned with planned resolutions.
| SEPD/048 | SEPD | DNOs, CVA Registrants, CVA Meter Operator Agents | SSEN Distribution enquired and then confirmed the meter commissioning processes carried out by a large meter operator was allowable per the BSC. This will go towards resolving Technical Assurance of Metering Audit Failures and therefore will increase confidence in reliability of High Accuracy Metering systems. | In progress | Elexon have agreed that the commissioning process is allowable per BSC, awaiting statement from relevant MOA to progress. | 04/2023 | This activity allows for a clarification to be issued by Elexon regarding the commissioning of CVA Metering Systems, increasing confidence in their reliability, when subject to audit. | N/A | No data is expected to be shared. Audit findings will be populated on Elexon systems whenever audits are carried out. | N/A | A positive impact for CVA Registrants, Meter Operators and CVA market confidence. This change will resolve existing audit failures. | Positive impact on SSEN as part of CVA registrant confidence in metering accuracy, and among industry relating to published audit findings. | Maintain alignment with Elexon and MOA to ensure publication of statement and resolution of applicable audit failures. | SSEN Distribution have a requirements as CVA Registrant to ensure accurate metering at GSPs, this initiative will increase confidence in SSEN's metering systems.
| SEPD/049 | SEPD | DNOs, Electricity Suppliers, Meter Operators | A DCUSA Change proposal was raised and progressed to allow DNOs to move supplier equipment as part of service alteration works, allowing for an improved customer journey. | In progress | The current business processes have been provisionally updated to allow for the expected changes. IT development is now required to update the SSEN Distribution system, PROMIS. | 06/2023 | This activity allows for a smoother process for the customer when requesting a service alteration. This also allows SSEN to continue delivering a trusted and positive service to our customers. | N/A | Customer service alteration applications will be received as normal, secondary quotes will be issued for DNO meter moves alongside service alteration works. | N/A | A positive impact for customers and greater efficiency for industry parties . | A potentially more complex level of work to be carried out as part of service alterations however would provide positive exposure for SSEN in improving customer journey. | Remain engaged with business change team to ensure successful delivery of system and process changes. | The DCUSA modification has been approved and this process is available to industry parties, therefore change activities will need to be completed to meet expected demand.
| SEPD/050 | SEPD | Regen, Isle of Wight Council | UN:LOCK - UNBLOCKING NETWORKS Local Optimisation, Consumers and Knowledge. UN:LOCK will look at ways in which the connection of new generation can be accelerated, within existing network capacity limits to help facilitate the Isle of Wight’s Net Zero aspirations | In progress | Concluding the discovery stage and preparing for Alpha stage. | 08/2023 | Coordination and cooperation being used to increase network capacity on the Isle of White. | https://www.ssen.co.uk/news-views/2024/SSEN-secures-funding-for-pioneering-new-innovation-project/ | N/A | N/A | Enable the development of more renewable electricity due to the increased capacity to export off the island. | Release additional capacity on the island enabling new connections. | Starting the Alpha stage of the project. | Next stage in the project, working towards integration into Business As Usual.
| SEPD/051 | SEPD | Baringa, GLA, University of Reading | MaxFlex involves the creation of Energy Flexibility Certificates, which will help firms, and Local Authorities, better understand the potential opportunities for them. | In progress | Concluding the discovery stage and preparing for Alpha stage. | 08/2023 | Making it easier for a range of stakeholders to participate in the flexibility markets. | https://www.ssen.co.uk/news-views/2024/SSEN-secures-funding-for-pioneering-new-innovation-project/ | N/A | N/A | Betters the ability of Local Authorities and the occupants of industrial and commercial properties to become involved in flexibility markets; | Increase the availability of flexibility on the network. | Starting the Alpha stage of the project. | Next stage in the project, working towards integration into Business As Usual.
| SEPD/052 | SEPD | Baringa, Centre for Sustainable Energy. | The Equal LCT project will identify and report the types of consumers being left behind in the energy transition as it relates to electricity networks. It will then analyse and document their related needs, and propose products and services designed to enable their participation in a just energy transition. | In progress | Formulating the commercial models with a view to having internal workshops in April, external workshops in May, and finalising in June. | 07/2023 | Enabling low carbon technologies for energy consumers who may be left behind in the transition. | N/A | N/A | N/A | Promotes an equitable transition while increasing liquidity in the flexibility markets, enabling low carbon technologies. | Increased liquidity of the flexibility market. | Apply for Alpha stage funding to conduct in depth trial design. | Project will be developed following the process outlined in SIF Governance document.
| SEPD/053 | SEPD | Department for Transport, National Highways, ENA, all 6 DNOs, MSA operators. | Guidance has been developed in partnership with the OZEV, providing a common approach for DNOs to provide optimum and efficient network solutions to facilitate the roll-out of MSA EV charging infrastructure. This capacity ramping approach provides: . Assurance that capacity will be available for anticipated future demand, as and when it is needed. . Application of use of system capacity charges in line with anticipated maximum usage as load grows. .A common framework that will be made available for use by other technologies/customer types. | In progress | Guidance has been developed and SSEN is currently waiting on formal applications of connection from MSAs. | 10/2022 | Efficiently uses resources to create capacity ahead of need, to accelerate the electrification of transport. | https://assets.publishing.service.gov.uk/media/6245ba40e90e075f15381cf0/taking-charge-the-electric-vehicle-infrastructure-strategy.pdf | N/A | N/A | Allow more connections and accelerate the transition to electric vehicles. | Having confidence to invest efficiently in network assets. | Start processing the formal applications for connection. | Better develop the internal processes.
| SEPD/054 | SEPD | GHD, Frontier Economics | Climate change poses new challenges when it comes to protecting assets. Nature4networks looks for alternative methods of protection, studying nature for the solutions it could offer, providing benefits when it comes to climate, biodiversity, and societal well-being. | In progress | Concluding the discovery stage and preparing for Alpha stage. | 08/2023 | Mitigating the impact of network assets on the environment. | SSEN Distribution secures funding for pioneering new innovation projects - SSEN | N/A | N/A | Ensures network assets are more sustainable. | Better and more sustainable defence of assets. | Starting the Alpha stage of the project. | Next stage in the project, working towards integration into Business As Usual.
| SEPD/055 | SEPD | ENA, all GB gas and electricity network organisations | Working as part of the ENA Open Networks whole system workstream to develop a guide for local authorities. | Completed | N/A | 09/2022 | Coordination and cooperation between network organisations to help develop energy decarbonisation plans for local authorities. | N/A | N/A | N/A | Helping create future energy plans for local authorities. | Increased knowledge of future network needs. | Continue cooperation. | Accelerated decarbonisation of energy systems and better understanding of network needs.
| SEPD/056 | SEPD | ENA, SPEN, ENWL, UKPN, NGED, NPG | SSEN took the lead in developing and launching a Whole Industry Collaboration Strategy between all GB DNOs. Our customers all have differing needs, and although geographically we solve these individually, there are shared objectives we understand we can solve better together, therefore, our Collaboration Strategy puts our customers first, working towards a common purpose to deliver what’s best for them. We agreed a set of key areas that we would collaborate on by default; Customer Satisfaction and Emerging Trends Supporting Customers in Need Resilience and Planning Joint Campaigning Customer Digitalisation and Data Sharing Supporting customers on the Transition to Net-Zero. | In progress | Ongoing meetings. | 10/2023 | Collaborating and coordinating with DNOs to ensure that customers are supported as the network develops. | N/A | N/A | N/A | Positive - better experience for energy consumers. | Positive - better understanding of where security and resilience should be built into the system. | Further delivery of key initiatives. | To ensure that customers are better supported.
| SEPD/057 | SHEPD | NGED, SPEN, NPG, ElectraLink | Flexible Power is both a collaboration agreement across 4 DNOs and an associated flexibility provider portal. The collaboration centres on aligning processes and terminology and workshopping aspects of flexibility operation. The portal is therefore a platform for flexibility service dispatching and settlement. | In progress | Monthly product delivery group meetings and ad hoc development demo calls when new features are added to the platform. | Collaboration began: 09/2020 Portal launched: 09/2023 | Collaboration among network operators to streamline the flexible service dispatching and settlement process. | Further information can be found in Reports on SSEN's Flexibility Services Document Library, particularly the SLC31E - SSEN 2022-23 Flexibility Services Procurement Report. | Data shared between flexibility providers and the DNOs to dispatch and settle services. Restricted sharing. | N/A | Positive; flexibility providers operating across more than one DNO's licence area only need to be onboarded to one platform. | Positive; supports automation of flexibility service dispatching, and all participating DNOs share the cost of platform, allowing for greater efficiencies. | Continued development of the platform to add more functionality, including making it easier for providers who can't connect via an API. | Making the platform more accessible will increase usage and help to standardise dispatching across a wider area.

## New Entries (hidden)
| Relevant coordination and cooperation activities | [14 empty] | Actions or Processes arising
Name of Project/Activity Owner | Unique ID | Licensee | Collaborating licensees and other stakeholders | Description of the coordination/ cooperation activity | Status | Latest stage /Update /comments (if any) | Coordination activity initiation date (mm/yyyy) | Whole system relevance of the activity | External links to reports on the activity (If available) | Description of data (who shared the data) [widely shared/restricted sharing] | External links for data (if available) | Impact of the activity on the whole system | Impact of the activity on licensee | Recommended next stage of the activity | Justification for recommendation | Action or Process description | Action or process initiation date (mm/yyyy) | Status | Reference of the activity or user suggestion which resulted in this action/process
|  | SEPD | Low Carbon Hub, University of Oxford, Oxfordshire and Oxford City Councils, Origami, Piclo, NuvveCorporation, EDF Energy | LEO is a collaborative DSO demonstrator project involving multiple partners. The objectives are to: (i) prove Investable Business Models; (ii) build a Community of Skilled Energy People in Oxfordshire; (iii) develop the Markets for DSO; (iv) develop the mapping tools for Local Area Energy Planning; and (v) trial Flexibility. | In progress | Report on the first Trial Period has been produced and submitted to Ofgem. | 2019-04-01 | This is a whole systems project, engaging all network licensees (including the ESO) via the ENA and interacting with Suppliers, Aggregators, Local Generation and Demand Sites. | Home - Project LEO (project-leo.co.uk) https://ssen-transition.com/ | There is a data sharing agreement within the project. The holder of the data is ultimately the University of Oxford. | N/A | The LEO project will enable us and other network operators to manage electricity networks more efficiently and flexibly at a local level through positive and broad engagement. | Positive impact through collaboration to enable the energy transition. | Next stages could include further work with councils to produce blueprint for LAEPs and more demonstrations of street level energy transition for those least able to afford it. | To further enable a Just Transition and to support councils contribute towards their Net Zero goals.
|  | SEPD | Low Carbon Hub, University of Oxford, Oxfordshire and Oxford City Councils, Origami, Piclo, NuvveCorporation, EDF Energy | [12 empty] | Looking to apply for SIF funding | 2022-09-01 | Mature | This project is building the proof of concept systems and processes to embed DSO in BaU for ED2
SEPD
Note on A12: Britten, Harry: Please enter name of project/activity owner from SSEN for future updates
Note on E12: Britten, Harry: Enter Collaborators as shown above
Note on F12: Britten, Harry: Short description of the activity. Enter any corresponding action in subsequent row as shown in example above (not necessary if no actions of note)
Note on R12: Britten, Harry: Only fill in for corresponding actions in row below main activity entry (as shown in above example). If no actions or processes arising then leave blank.

## User suggestions
Details of all proposals received during a relevant period from system users to advance the efficient and economical operation of Electricity Distributors’ and/or transmission owners’ networks. Details of any system user proposals that have been implemented (or are being implemented) as well as a concise and clear summary of proposals not deemed to be apt for implementation, including the reason(s) for that decision.
Unique id | Licensee | Collaborating licensees | User category | Suggestion submission date (mm/yyyy) | Description of the suggestion | Whole system relevance | Description of the action taken on the suggestion | Justification of the action
SEPD/037 | SEPD | All 6 DNOs, the ESO, WSP. | Network operators | 10/2023 | Project Commander Identifies and defines alternative the ESO/DSO coordination schemes for accessing and managing DERs with respect to their qualification, procurement, dispatch and settlement. In particular, the roles and responsibilities of the key actors involved, their high-level interfaces across different timescales and information exchanges as well as key market arrangements to facilitate the process. Quantify and assess the techno-economic feasibility of alternative the ESO/DSO coordination schemes for accessing and managing DERs for service provision at operational timescales Develop an engineering-based roadmap and recommendations for the practical implementation of the preferred the ESO/DSO coordination scheme. | Improved coordination by information sharing between DNOs and the ESO by establishing channels of communication. | Participated in a series of workshops. | Help inform all coordination for data sharing activities.
SEPD/038 | SEPD | The ESO | Network operators | 02/2024 | PODE trying to build a better cross industry view of potential outage plans across both the Transmission and Distribution networks and how we can get a better wider organisation view of that and share the associated data so that all parties can make more informed and data driven decisions around outage plans to become more joined up and effective. | Means whole systems outage planning will be possible. | Early stages. The project has been initiated and meeting has taken place with the ESO. | Better coordination of outage planning.
SEPD/039 | SEPD | The ESO | Network operators | 10/2023 | The DER visibility project aims to increase the visibility of DERs and CERs for electricity system and network operators. | Due to this, visibility operators will have the ability to improve the operation of the whole-energy system. | 6 online workshops and 1 in person workshop have taken place. | More efficient operation of network. Better flexibility market access and liquidity, more informed decision making.
SEPD/010 | SEPD | The ESO, NGED | Network operators | 05/2021 | This is an Alpha Stage SIF project involving multiple parties exploring the potential for domestic flexibility services. CrowdFlex explores how domestic flexibility can be used in grid operations to help align demand to generation, improve coordination across the network, reduce stress on the system, while empowering consumers to be active players through new tariffs and incentives. | This involves multiple industry stakeholders to develop a broad-based approach to the complex issue of domestic flexibility. The project scope has also expanded to include issues in SHEPD area including considerations around Load Managed Areas. | SEPD are a partner in the successful Alpha project which closed in March 2023. The Beta application was approved by Ofgem in July 23. Beta project commenced in October 2023 and partners are preparing for the first round of trials summer 2024. | This builds on earlier innovation work delivered collaboratively by SEPD and the ESO, with the ultimate objective being to establish domestic flexibility as a reliable resource for network management.